4/17/02

WHOIS TF Conference Call

Attendees:

Sarah Andrews

Marilyn Cade

Laurence Djolakian

Karen Elizaga

Kristy McGee

Steve Metalitz

Ram Mohan

Hakikur Rahman

Thomas Roessler

Miriam Sapiro

Regrets: Tony Harris, Troy Dow, Abel Wisman

Other members did not respond/or confirm unavailability

Glen and Marie were not available to take minutes. Marilyn’s notes follow but are very summary.

Marilyn noted Tony’s apologies due to a board meeting conflict. she noted that the purpose of the meeting/conference call is to review whether all members have their assignments, have downloaded their files, understand their assignments, and are making progress. Tony Harris has completed his assigned 150 responses, and his submission is the most complete to date. Several members of the TF were just beginning their download, analysis, etc.  The call today was to allow questions to the Editorial/technical team.

Marilyn turned the call over to Thomas to lead discussion about the process.

Abel Wisman was not on the call, but had previously advised Marilyn, Kristy, Thomas, and Tony that his work on Q20 is complete but needs to be made “user friendly” and that is work in progress. He is evaluating all free form responses to Q.20.

General Problems Discussion:

No questions from group on general problems.

Q7. MSC : only done about 50 of 150.  Kristy, Hakikur, MSC: in agreement on Q7.

7b) no additional comment

8) some gems from reading so far

10) people seem not to understand question. Should examine this further as others “read”.

Laurence volunteered to do the French responses which people have.

13,14,15, Thomas will change the instruction log per the discussion.

Deadline: 4/24.

Discussion: Steve and others have not begun to analyze. Several members not on call. Registry reps are making a strong effort to read their initial assignment and deal with additional requested analysis of 300 more. Hard to do. Registries not even on call. Marilyn to contact them.

Marilyn:  Allocate certain time frame to complete specific functions.  There are time limits which we need to meet. Not only task of TF to analyze survey. Getting lost in that.  MUST get a report done in a reasonable time frame to accept comments before Romania.  Steve raised questions about time frames. Noted unclear.

Marilyn: We talked about timeframes last call. Many not on call. Understand is confusing. Lack resources to do a lot of outreach if people not on calls.

Important to remember that it isn’t just reading, but getting into format for analysis.  Understand that may not be feasible to analyze all narratives IF individual groups don’t/can’t meet goals.

Marilyn asked Thomas to discuss time frames for analysis and what he can manage, given other commitments.

Steve: Hasn’t begun reading his assignment. Not clear can read all 150/complete assignment.

Marilyn: understand concern about calendar. However, the TF has some joint responsibility for what it has agreed to do. She will poll the group, online, for their views on completing their assignment.

Tony has completed his assignment.

Marilyn intends to read her 150, although is a serious challenge.

Kristy: she is doing other work on analysis; will complete her assignment.

Steve: unlikely can do all

Laurence: will do her best

Miriam: do her best

Hakikur. Same

Karen: same

Ram: had dropped by then.

Troy: Marilyn had spoken to. Not sure can complete, but intends to try to do some at least.

Next Steps: Design of draft final report. Marilyn described the process she and Tony envisioned for the draft final report and associated time frames. Steve requested a detailed tentative time line. Marilyn noted that was important and that she and Tony would collaborate on with the Editorial Team. Steve wanted to know the firm dates.  Laurence noted that although we did our best in drafting in Accra on site on what we presented in view graph form, she preferred not to have similar situation in Romania.  All agreed to need to have final DRAFT before traveling. Marilyn noted that she starts traveling 6/19 and asked for view of who will be in  Romania.

Short list:

Tony:  not on call/not sure

Marilyn: yes

Sarah: not sure

Glen: yes

Laurence: not sure

Karen: yes?

Kristy: working on it/not sure

Steve: yes

Ram: yes

Hakikur: not sure

Thomas: not sure to unlikely

Miriam: yes

Abel: plans to drive/per discussion with MSC/likely

Others whom Marilyn expects:

Tim: likely

Troy: not likely

Bret: not sure

Philipp: likely

Oscar: not sure

Ken: likely

Thomas will develop a draft of the skeleton for response, similar to last time. Then Teams will be assigned drafting by Marilyn and Tony.  Question: same teams or changes?  Marilyn: we will make some changes, due to changes in participation. Tony and I will make a draft assessment and circulate.

URGENT, URGENT:

Submissions of content analysis, to be considered, must be delivered by 4/24.  Please do your best to have your submissions in by then!!!!

Submit whatever you have by then. We will look at and where we have to, will extrapolate We can note that not all constituencies were able to deliver their analysis by the date needed. We need to have final results by mid May.

Thomas will develop a skeleton, similar to the last skeleton, by May 1.  Marilyn and Tony will assign analysis on the various questions and ask that you draft preliminary findings on your sections.

Note: No results after 5/1 will be helpful. All results by 4/24 will be included. Results between 4/24 and 5/1 may not be included.

Proposed approach: WE deliver analysis; Thomas, Abel, Kristy “crunch” the data. WE get Thomas’ skeleton 5/1; Marilyn and Tony make assignments for drafting. Circulate. Have a discussion call/maybe two. Post final draft report for public comment. Allow 3 weeks for comments. Review. Assess how to incorporate additional feedback. During three week period, listening sessions take place.

Make recommendations about next steps for TF and other initiatives related to WHOIS.

Calendar to follow as separate posting to TF.

Listening sessions:

- GAC

- Law Enforcement

- ICANN staff

- privacy representatives

- various groups who use WHOIS

Marilyn to draft outline of listening sessions and post…

Call ended

Next call: 5/8

--please use email, or call Marilyn or Tony with questions in meantime.

Marilyn Cade, co-chair.